## Aug
Date | Developer | Tracking | Project | Activity | Description | BugFix
2016-08-01 | Akshay Patel | 8 | Piaggio | Training | Training | no
2016-08-02 | Akshay Patel | 8 | Piaggio | piaggio dropdown auto fill data on carrello page | piaggio dropdown auto fill data on carrello page | no
2016-08-03 | Akshay Patel | 8 | Piaggio | Adding functionality for add attributes from admin | Adding functionality for add attributes from admin | no
2016-08-04 | Akshay Patel | 8 | Piaggio | Adding functionality for add attributes from admin | Adding functionality for add attributes from admin | no
2016-08-05 | Akshay Patel | 8 | Piaggio | Adding functionality for add attributes from admin | Adding functionality for add attributes from admin | no
2016-08-08 | Akshay Patel | 8 | Piaggio | Training | Training | no
2016-08-09 | Akshay Patel | 8 | Piaggio | Training | Training | no
2016-08-10 | Akshay Patel | 8 | Piaggio | attributes value store in database from carrello page. | attributes value store in database from carrello page. | no
2016-08-11 | Akshay Patel | 8 | Piaggio | incompatibility module admin | incompatibility between all attributes which is managed by admin | no
2016-08-12 | Akshay Patel | 8 | Piaggio | incompatibility module admin | incompatibility between all attributes which is managed by admin | no
2016-08-13 | Akshay Patel | 8 | Piaggio | bug fix of carrello page attributes fields | bug fix of carrello page attributes fields | yes
2016-08-15 | Akshay Patel | 8 | Piaggio | Training | Training | no
2016-08-16 | Akshay Patel | 8 | Piaggio | Training | Training | no
2016-08-17 | Akshay Patel | 8 | Piaggio | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | no
2016-08-19 | Akshay Patel | 8 | Piaggio | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | no
2016-08-22 | Akshay Patel | 8 | Piaggio | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | Delivered incompatibility module with adding data of attributes and incompatibility from admin side | no
2016-08-23 | Akshay Patel |  | Piaggio | Fix graphic interface press center | Fix graphic interface press center | no
2016-08-24 | Akshay Patel | 8 | Piaggio | Show the options (formato carta, grammatura, ecc) from interface | Show the options (formato carta, grammatura, ecc) from interface | no
2016-08-24 | Akshay Patel | 8 | Piaggio | Add the field in the “Foglio di accompagnamento” . [attached the document to see the sheet] | Add the field in the “Foglio di accompagnamento” . [attached the document to see the sheet] | no
2016-08-25 | Akshay Patel | 8 | Piaggio | Interface side cart Print Center "Piaggio" so that the options selected by the user “Piaggio” are not mandatory in all cases. | Interface side cart Print Center "Piaggio" so that the options selected by the user “Piaggio” are not mandatory in all cases. | no
2016-08-26 | Akshay Patel | 8 | Piaggio | MANDATORY FIELD TASK with adding functionality in admin | new requirements of edit product page, and display only selected fields on carello page for each product. | no
2016-08-29 | Akshay Patel | 8 | Piaggio | ticket solution 10012 - 10013 | ticket solution 10012 - 10013 | yes
2016-08-30 | Akshay Patel | 8 | Piaggio | ticket solution 10016,10017 | ticket solution 10016,10017 | yes
2016-08-31 | Akshay Patel | 8 | piaggio | ticket solution 10018 | ticket solution 10018 | yes

## Sept
Date | Developer | Tracking | Project | Activity | Description | BugFix
2016-09-05 | Akshay Patel | 4 | Bucap | configure code with ms sql configuration | configure code with ms sql configuration | no
2016-09-05 | Yogesh Dobariya | 4 | Bucap | configure code with ms sql configuration | configure code with ms sql configuration | no
2016-09-06 | Akshay Patel | 4 | Bucap | Bucap static page completed | Bucap static page completed | no
2016-09-06 | Yogesh Dobariya | 3 | Bucap | Bucap- comune di bologna pages(html) | Bucap- comune di bologna pages(html) | no
2016-09-06 | Dakshay Khalasi | 3 | Bucap | making 2 pages for Comune Bologna | making 2 pages for Comune Bologna | no
2016-09-07 | Akshay Patel | 4 | Bucap | Bucap static page changes completed | Bucap static page changes completed | no
2016-09-07 | Dakshay Khalasi | 4 | Bucap | Bucap static page changes completed | Bucap static page changes completed | no
2016-09-07 | Dakshay Khalasi | 4 | Bucap | Yii framework code study | Yii framework code study | no
2016-09-07 | Yogesh Dobariya | 2 | Bucap | pc set up(sql server 2008) for bucap project | pc set up(sql server 2008) for bucap project | no
2016-09-07 | Yogesh Dobariya | 1 | Bucap | access sql server in ubuntu | access sql server in ubuntu | no
2016-09-08 | Akshay Patel | 5 | Bucap | setup windows and setup code with mssql on it and started working on ticket module | setup windows and setup code with mssql on it and started working on ticket module | no
2016-09-08 | Chinjan Patel | 8 | Bucap | setup windows and setup code with mssql on it and started working on ticket module | setup windows and setup code with mssql on it and started working on ticket module | no
2016-09-08 | Dakshay Khalasi | 8 | Bucap | setup windows and setup code with mssql on it and started working on ticket module | setup windows and setup code with mssql on it and started working on ticket module | no
2016-09-08 | Akshay Patel | 3 | Gestione Gettoni | new code intigration and attiva module continue | new code intigration and attiva module continue | no
2016-09-08 | Yogesh Dobariya | 8 | Gestione Gettoni | study new assigned task and implement excel file import in core php | study new assigned task and implement excel file import in core php | no
2016-09-08 | Dakshay Khalasi | 4 | Bucap | setup windows machine and installed required s/w for bucap. | setup windows and setup code with mssql on it and started working on ticket module | no
2016-09-09 | Akshay Patel | 8 | Gestione Gettoni | Ticket attiva field task | Ticket attiva field task | no
2016-09-09 | Yogesh Dobariya | 2 | Gestione Gettoni | Bug to add a new field in progetto and tickets sections | Bug to add a new field in progetto and tickets sections | no
2016-09-09 | Yogesh Dobariya | 4 | Gestione Gettoni | study excel sheet and database and setup project in windows | study excel sheet and database and setup project in windows | no
2016-09-09 | Yogesh Dobariya | 2 | Gestione Gettoni | compare excel sheet and database and setup project in windows | compare excel sheet and database and setup project in windows | no
2016-09-09 | Dakshay Khalasi | 2 | Bucap | access sql server and setup code | access sql server and setup code | no
2016-09-09 | Dakshay Khalasi | 6 | Bucap | Bucap code study | Bucap code study | no
2016-09-10 | Akshay Patel | 6 | Gestione Gettoni | bug fix and code delivered | bug fix and code delivered | yes
2016-09-10 | Yogesh Dobariya | 8 | Gestione Gettoni | study Gestoine Project | study Gestoine Project | no
2016-09-10 | Chinjan Patel | 8 | Gestione Gettoni | study Gestoine Project and code integration | study Gestoine Project and code integration | no
2016-09-10 | Dakshay Khalasi | 8 | Gestione Gettoni | study Gestoine Project | study Gestoine Project | no
2016-09-12 | Akshay Patel | 8 | Bucap | faldoni dinamic module | faldoni dinamic module | no
2016-09-12 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-12 | Chinjan Patel | 8 | Bucap | Integration of code in local pc and code study | Integration of code in local pc and code study | no
2016-09-12 | Dakshay Khalasi | 8 | Bucap | Integration of code in local pc ,code study and faldoni dinamic module integration | Integration of code in local pc ,code study and faldoni dinamic module integration | no
2016-09-13 | Akshay Patel | 8 | Bucap | update dynamic faldoni data entry in database, display listing, | update dynamic faldoni data entry in database, display listing, | no
2016-09-13 | Yogesh Dobariya | 8 | Gestione Gettoni | insert field in database | insert field in database | no
2016-09-13 | Chinjan Patel | 2 | Bucap | Integration on local machine and code study | Integration on local machine and code study | no
2016-09-13 | Chinjan Patel | 6 | Bucap | View file Integration | View file Integration | no
2016-09-14 | Akshay Patel | 8 | Bucap | dynamic module edit, search, validation | dynamic module edit, search, validation | no
2016-09-14 | Dakshay Khalasi | 8 | Bucap | Barcode view page Integration | Barcode view page Integration | no
2016-09-14 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-14 | Chinjan Patel | 8 | Bucap | Barcode view page Integration | Barcode view page Integration | no
2016-09-14 | Dakshay Khalasi | 8 | Gestione Gettoni | insert field in database | insert field in database | no
2016-09-15 | Akshay Patel | 4 | Gestione Gettoni | Gettoni ticket solution database | Gettoni ticket solution database | no
2016-09-15 | Dakshay Khalasi | 8 | Gestione Gettoni | Gettoni ticket module code study | Gettoni ticket solution database | no
2016-09-16 | Akshay Patel | 4 | Gestione Gettoni | Creation interface to view hierarchic ticket | Creation interface to view hierarchic ticket | no
2016-09-16 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-19 | Yogesh Dobariya | 3 | Gestione Gettoni | changes in import excel file | changes in import excel file | no
2016-09-19 | Yogesh Dobariya | 5 | Gestione Gettoni | set cron job for import file | set cron job for import file | no
2016-09-19 | Akshay Patel | 3 | Gestione Gettoni | ticket hierarchic module | ticket hierarchic module | no
2016-09-19 | Akshay Patel | 5 | Piaggio | new changes | new changes | no
2016-09-20 | Akshay Patel | 2 | Piaggio | piaggio carrello page changes | piaggio carrello page changes | no
2016-09-20 | Akshay Patel | 6 | Piaggio | add attribute page changes | add attribute page changes | no
2016-09-20 | Yogesh Dobariya | 8 | Gestione Gettoni | set cron job for import file | set cron job for import file | no
2016-09-20 | Chinjan Patel | 8 | Bucap | add document button functionality | add document button functionality | no
2016-09-20 | Dakshay Khalasi | 8 | Bucap | remove document button functionality | remove document button functionality | no
2016-09-21 | Akshay Patel | 3 | Gestione Gettoni | changes on ticket page(ticket hierarchic) | changes on ticket page(ticket hierarchic) | no
2016-09-21 | Akshay Patel | 5 | Bucap | changes of image 4 & 5 | changes of image 4 & 5 | no
2016-09-21 | Chinjan Patel | 8 | Bucap | remove (minus button) document functionality | remove (minus button) document functionality | no
2016-09-21 | Yogesh Dobariya | 8 | Gestione Gettoni | set cron job for import file | set cron job for import file | no
2016-09-21 | Dakshay Khalasi | 8 | Bucap | remove document functionality | remove document functionality | no
2016-09-22 | Akshay Patel | 3 | Gestione Gettoni | ticket hierarchic completion | ticket hierarchic completion | no
2016-09-22 | Akshay Patel | 5 | Piaggio | piaggio changes on attribute page | piaggio changes on attribute page | no
2016-09-22 | Dakshay Khalasi | 8 | Bucap | modifica documento page integration | modifica documento page integration | no
2016-09-22 | Yogesh Dobariya | 8 | Gestione Gettoni | study the relationship in database and implement | study the relationship in database and implement | no
2016-09-22 | Chinjan Patel | 8 | Bucap | dropdown code integration (modifica documento page) | dropdown code integration (modifica documento page) | no
2016-09-22 | Dakshay Khalasi | 8 | Bucap | modifica documento page integration | modifica documento page integration | no
2016-09-23 | Akshay Patel | 4 | Piaggio | piaggio changes 'add CHECKBOX after FINITURA selected' on attribute page piaggio | piaggio changes 'add CHECKBOX after FINITURA selected' on attribute page piaggio | no
2016-09-23 | Akshay Patel | 4 | Piaggio | add checkbox on carello page piaggio | add checkbox on carello page piaggio | no
2016-09-23 | Yogesh Dobariya | 8 | Gestione Gettoni | implement relationship in database and changes in import excel file according to relationship | implement relationship in database and changes in import excel file according to relationship | no
2016-09-23 | Chinjan Patel | 6 | Bucap | modifica documento page integration changes | modifica documento page integration | no
2016-09-23 | Chinjan Patel | 2 | Bucap | share sql server database with more local machine to work with | share sql server database with more local machine to work with | no
2016-09-24 | Akshay Patel | 2 | Piaggio | ticket section testing | ticket section testing | yes
2016-09-24 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-26 | Akshay Patel | 4 | Gestione Gettoni | ticket viewer changes | ticket viewer changes | no
2016-09-26 | Akshay Patel | 4 | Gestione Gettoni | code import cronjob | code import cronjob | no
2016-09-26 | Chinjan Patel | 6 | Gestione Gettoni | Ticket module study | Ticket module study | no
2016-09-26 | Yogesh Dobariya | 3 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-26 | Yogesh Dobariya | 5 | Gestione Gettoni | check cronjob on hostgator | check cronjob on hostgator | no
2016-09-26 | Dakshay Khalasi | 8 | Gestione Gettoni | Ticket module study | Ticket module study | no
2016-09-27 | Yogesh Dobariya | 6 | Gestione Gettoni | implement send email when excel heder change in import excel file | implement send email when excel heder change in import excel file | no
2016-09-27 | Yogesh Dobariya | 2 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-27 | Dakshay Khalasi | 8 | Gestione Gettoni | Ticket module study | Ticket module study | no
2016-09-28 | Akshay Patel | 8 | Bucap | bucap changes | bucap changes | no
2016-09-28 | Dakshay Khalasi | 8 | Bucap | bucap changes | bucap changes | no
2016-09-28 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-28 | Chinjan Patel | 8 | Bucap | home page changes of showing documento | home page changes of showing documento | no
2016-09-28 | Dakshay Khalasi | 8 | Bucap | home page changes of showing documento | home page changes of showing documento | no
2016-09-29 | Yogesh Dobariya | 8 | Gestione Gettoni | implement export excel file using different method | Continue import excel file | no
2016-09-29 | Chinjan Patel | 8 | Bucap | Continue home page changes of showing documento | Continue home page changes of showing documento | no
2016-09-30 | Yogesh Dobariya | 8 | Gestione Gettoni | Continue import excel file | Continue import excel file | no
2016-09-30 | Chinjan Patel | 8 | Bucap | Continue home page changes of showing documento | Continue home page changes of showing documento | no
2016-09-30 | Dakshay Khalasi | 8 | Bucap | Continue home page changes of showing documento | Continue home page changes of showing documento | no

## Oct
Date | Developer | Tracking | Project | Activity | Description | BugFix
2016-10-03 | Akshay Patel | 2 | Bucap | Barcode auto populate task on censimento manuale page | 2nd Database (user) create and intrigrate and started working on barcode auto populate task | no
2016-10-03 | Chinjan Patel | 4 | Bucap | Faldoni page (datatable) | Faldoni page changes (datatable of documento) | no
2016-10-04 | Akshay Patel | 8 | Bucap | Censimento manual changes | Censimento manual changes - autofill on barcode search | no
2016-10-04 | Chinjan Patel | 6 | Bucap | Faldoni page al_date and del_date integration | Faldoni page al_date and del_date integration | no
2016-10-05 | Akshay Patel | 8 | Bucap | Cencimmento manual page task | Cencimmento manual datafill, index-recerca and update data complete | no
2016-10-05 | Dakshay Khalasi | 4 | Bucap | Faldoni page date picker for date | Faldoni page date picker for al date and del date integration | no
2016-10-06 | Akshay Patel | 4 | Bucap | PG criteria filter and index date filter bugfix | PG criteria filter and ndex date filter bugfix | yes
2016-10-06 | Yogesh Dobariya | 4 | Bucap | Made document for importer/exporter | Made document for importer/exporter | no
2016-10-06 | Chinjan Patel | 8 | Bucap | Censimento manuale page and data censimento changes | Censimento manuale page changes and data censimento date picker issue solved. Code delivered | no
2016-10-07 | Yogesh Dobariya | 3 | Bucap | Made document for not display field in gestonigettoni | Made document for not display field in gestonigettoni | no
2016-10-07 | Chinjan Patel | 2 | Bucap | Censimento pratica page view change | Censimento pratica page view change | no
2016-10-07 | Chinjan Patel | 8 | Bucap | Gestione documenti page integration | Gestione documenti page integration | no
2016-10-07 | Chinjan Patel | 6 | Bucap | Gestione documenti page integration | Gestione documenti page integration | no
2016-10-10 | Yogesh Dobariya | 5 | Gestione Gettoni | hide and make document for not display field | Hide and make document for not display field (azienda, prodotto, acttivita) | no
2016-10-12 | Yogesh Dobariya | 3 | Gestione Gettoni | hide and make document for not display field | Hide and make document for not display field (azienda, prodotto, acttivita) | no
2016-10-14 | Chinjan Patel | 6 | Bucap | Faldone page changes | Faldone page changes of disable-archive faldoni | no
2016-10-15 | Chinjan Patel | 6 | Bucap | Faldone page changes | Faldone page changes of display field anno padre & pg padre | no
2016-10-17 | Akshay Patel | 4 | Bucap | Cencimento manuale page changes | Cencimento manuale changes of pg size 7 digit and autofill sirie | no
2016-10-18 | Yogesh Dobariya | 5 | Gestione Gettoni | Setup gesttonigettoni in windows server and test | setup gesttonigettoni in windows server and test | no
2016-10-18 | Chinjan Patel | 8 | Bucap | Censimento manuale page changes | Censimento manuale page delete faldone | no
2016-10-19 | Yogesh Dobariya | 4 | Gestione Gettoni | Test and solve tracking module | test tracking module and upload changes on windows server | no
2016-10-19 | Chinjan Patel | 8 | Bucap | Delete faldone | Delete faldone and delete relational data | no
2016-10-20 | Yogesh Dobariya | 6 | Gestione Gettoni | Solve bug and upload on hostgator | solve bug in gesttonigettoni project , upload on hostgator and testing | no
2016-10-28 | Dakshay Khalasi | 3 | Bucap | Testing deadlock | Testing deadlock when multiple users inserts data | yes
2016-10-28 | Chinjan Patel | 8 | Bucap | Pratica page eliminato button functionality | Censimento pratica page eliminato button functionality | no
2016-10-28 | Yogesh Dobariya | 8 | Gestione Gettoni | Insert the item “Importa rendicontazione” | Insert the item “Importa rendicontazione” under the menu “Gestione” on top | no

## Nov
Chinjan Patel | Developer | Tracking | Project | Activity | Description | BugFix
2016-11-03 | Akshay Patel | 8 | Gestione Gettoni | Added Filter search | Added filters of Chiusi, Numero attività and Escalati | no
2016-11-07 | Akshay Patel | 2 | Gestione Gettoni | New task study and create database | New task study and create database | no
2016-11-08 | Akshay Patel | 2 | Gestione Gettoni | New menu items | Added 7 new menu items | no
2016-11-09 | Akshay Patel | 8 | Gestione Gettoni | Worked on new modules | Worked on new modules of menu items, uploaded code and live testing | no
2016-11-09 | Chinjan Patel | 3 | Bucap | Home page added columns | Home page added 5 columns of data stato | no
2016-11-09 | Chinjan Patel | 5 | Bucap | Home page filter | Home page filter for stato date | no
2016-11-09 | Yogesh Dobariya | 2 | Gestione Gettoni | Added filter in ticket section | Added filter in ticket section | no
2016-11-10 | Chinjan Patel | 4 | Bucap | Home page filter for stato date and datatabel sorting | Home page filter for stato date and datatabel sorting for pratica table issue solved | no
2016-11-10 | Yogesh Dobariya | 4 | Cedacri | Added filter in ticket section | Added filter in ticket section | no
2016-11-10 | Yogesh Dobariya | 4 | Gestione Gettoni | Menu changes | 7 Menu changes as required | no
2016-11-11 | Chinjan Patel | 1 | Cedacri | New code integration | New code integration | no
2016-11-12 | Chinjan Patel | 8 | Cedacri | New filters integration | Fiilter of Proprietario, Creazione and Chiusura added | no
2016-11-14 | Chinjan Patel | 8 | Cedacri | Fiilter of Proprietario dropdown changes | Fiilter of Proprietario dropdown changed to pop up window | no
2016-11-15 | Chinjan Patel | 8 | Cedacri | Fiilter of Proprietario dropdown changes | Fiilter of Proprietario dropdown changed to pop up window | no
2016-11-16 | Yogesh Dobariya | 8 | Gestione Gettoni | Opening ticket | Opening ticket and Static Graph Mockup | no
2016-11-17 | Akshay Patel | 2 | Gestione Gettoni | Chart integration | Chart integration on dashboard | no
2016-11-17 | Yogesh Dobariya | 8 | Gestione Gettoni | Static Graph Mockup and Import Excel CSV file | Static Graph Mockup and Import Excel CSV file | no